# Arkansas Political History Project

## Daily Build Log — 2025-03-26

### 1. What We Worked On Today

Established the foundational direction for the Arkansas Political History Project.

Defined the project as a long-term, evidence-based historical system rather than a traditional website.

Outlined a modular architecture prioritizing provenance, claims-based knowledge, and additive history.

Decided to build an externalized “Brain of the Build” using versioned markdown files as the project’s cognitive memory.

### 2. New Decisions Made

- Decision: Build a markdown-based external memory system for the entire project.

- Rationale: Prevent loss of institutional memory, enable transparent evolution of ideas, and support long-term historical integrity.

- Implications: All future work must be documented daily and logged additively.

- Affected Modules: Entire project.

- Confidence Level: High.

### 3. New Concepts / Frameworks Introduced

- “Brain of the Build”: A living, versioned markdown archive serving as the project’s cognitive system.

- Additive cognition: New understanding accumulates without erasing prior thinking.

- Claims-based history as the core organizing principle.

### 4. Changes to Prior Thinking

This formalized earlier discussions into a strict, versioned documentation system rather than ad hoc notes.

### 5. Open Questions Identified

- How granular community impact data should be at the earliest historical periods.

- How to best represent Indigenous governance prior to statehood within a claims-based framework.

### 6. Risks / Watchouts

- Risk of documentation fatigue if daily logs are skipped.

- Risk of overconfidence in early structural assumptions without sufficient historical testing.

### 7. Action Items for Next Session

- Begin defining historical eras and periodization for Arkansas.

- Start the Constitution module with territorial governance and the 1836 Constitution.

- Create initial provenance and claims model documentation.

### 8. Source Notes

No primary sources ingested today; structural and conceptual work only.

### 9. Meta Notes

This day establishes the intellectual scaffolding for the entire project. Getting this right early prevents systemic failure later.