# Arkansas Political History Project

## Daily Build Log — 2025-03-28

### 1. What We Worked On Today

Launched the Constitution module.

Documented territorial governance and the Arkansas Constitution of 1836.

Focused on power structures, exclusions, and institutional design rather than just legal text.

### 2. New Decisions Made

- Decision: Treat constitutions as political artifacts, not neutral documents.

- Rationale: Constitutional language reflects power relationships and social hierarchy.

- Implications: All constitutional analysis must include power and exclusion analysis.

- Affected Modules: Constitution, power modeling, community impact.

- Confidence Level: High.

### 3. New Concepts / Frameworks Introduced

- “Constitution as power architecture.”

- Distinction between formal structure and lived governance.

- Exclusion as an intentional design feature.

### 4. Changes to Prior Thinking

Shifted from a document-centric approach to a power-centric constitutional analysis.

### 5. Open Questions Identified

- How to quantify constitutional exclusion for comparative analysis.

- How to document Indigenous governance transitions during statehood.

### 6. Risks / Watchouts

- Political sensitivity around racialized constitutional analysis.

- Risk of anachronistic judgment if context is not clearly stated.

### 7. Action Items for Next Session

- Add source citations for territorial and 1836 materials.

- Begin Constitution of 1861 (Secession).

- Define a standard template for each constitution.

### 8. Source Notes

Primary sources to be added: constitutional texts, convention records, federal statutes.

### 9. Meta Notes

This session anchors the project in substance. From here on, everything connects to real historical decisions and consequences.